## RiskRegister1
Risk # | Date | The Risk of/That | Caused by | Resulting In | Consequence/Impact | Likelihood Score | Impact Score | Risk Score | Priority (H, M, L) | Mitigation | Risk Owner | Open/Closed
1 |  | Infrastructure upgrade costs for logistics technology | Need to upgrade systems to support operations | Increased project costs | Financial pressure | 3 | 2 | 6 | L | Plan phased IT upgrades and control spending | IT Manager
2 |  | Vendor switching costs for logistics service providers | Dependence on external logistics vendors | Transition and integration costs | Financial strain | 3 | 4 | 12 | L | Negotiate long-term vendor contracts | Procurement Manager
3 |  | Logistics operating costs in human capital and warehouse infrastructure | Expansion of logistics operations | Higher operating expenses | Reduced profit margins | 5 | 6 | 30 | M | Automate warehouse operations and optimize labor | Supply Chain Manager / HR
4 |  | Margin reduction due to price competition | Competitors offering lower fulfillment prices | Pressure to reduce pricing | Profit decline | 9 | 8 | 72 | H | Improve cost efficiency and pricing strategy | Finance Manager
5 |  | Capital investment in logistics infrastructure | Warehouse and technology expansion | Large capital expenditure | Financial pressure | 5 | 9 | 45 | H | Phase logistics infrastructure investment | Finance Director
6 |  | Process adjustments in fulfillment workflow | Implementation of new logistics processes | Operational disruption | Reduced operational efficiency | 3 | 1 | 3 | L | Train staff and standardize workflows | Operations Manager
7 |  | Limited human capital to support logistics operations | Shortage of logistics workforce | Operational capacity constraints | Reduced fulfillment efficiency | 5 | 2 | 10 | L | Recruit and train logistics staff | HR Manager
8 |  | Third-party warehouse and delivery partner dependency | Reliance on external logistics providers | Coordination challenges | Supply chain vulnerability | 5 | 4 | 20 | M | Diversify logistics partners | Supply Chain Manager
9 |  | Integration between logistics systems and e-commerce platform | Complex integration between systems | Operational disruption | Service inefficiencies | 7 | 6 | 42 | H | Conduct phased system integration | Technology Director
10 |  | Fulfillment network disruption during peak demand periods | High order volumes exceeding logistics capacity | Delayed order fulfillment | Customer dissatisfaction | 7 | 8 | 56 | H | Improve demand forecasting and warehouse capacity | Logistics Manager
11 |  | System failure or fulfillment network downtime | Operational or technical breakdown | Fulfillment interruption | Operational disruption | 3 | 9 | 27 | M | Implement redundancy and disaster recovery systems | IT Operations Manager
12 |  | Limited competitive pressure from small platforms | Small competitors lacking logistics capabilities | Minimal market disruption | Positive market position | 3 | 1 | 3 | L | Continue logistics innovation | Strategy Manager
13 |  | Competitor promotional campaigns | Aggressive competitor marketing | Loss of potential merchants | Competitive pressure | 5 | 2 | 10 | L | Strengthen merchant marketing programs | Marketing Manager
14 |  | Competitors introducing improved fulfillment capabilities | Competitors investing in logistics technology | Reduced competitive advantage | Market share pressure | 5 | 4 | 20 | M | Enhance fulfillment capabilities | Strategy Manager
15 |  | Competitors offering faster or lower-cost fulfillment services | Efficient competitor logistics networks | Price and service pressure | Competitive disadvantage | 7 | 6 | 42 | H | Improve logistics efficiency | Strategy Manager
16 |  | Cost of lagging behind competitors with advanced logistics networks | Competitors with mature fulfillment systems | Competitive disadvantage | Merchant migration risk | 7 | 8 | 56 | H | Invest in logistics innovation | Strategy Director
17 |  | Strong market competition from platforms with mature logistics networks | Competitors such as Amazon | Loss of competitive advantage | Loss of market share | 9 | 9 | 81 | H | Strengthen logistics ecosystem and merchant support | Strategy Director
18 |  | End-to-end commerce solution improving user experience | Integrated commerce platform | Improved service delivery | Positive brand reputation | 7 | 1 | 7 | L | Maintain service reliability | Customer Experience Manager
19 |  | Dissatisfaction due to delivery delays | Slow fulfillment performance | Customer complaints | Reputation damage | 5 | 4 | 20 | M | Improve delivery performance | Customer Experience Manager
20 |  | Logistic system and service failure affecting user experience | Operational or technical disruptions | Delivery errors | Brand reputation damage | 5 | 8 | 40 | H | Strengthen monitoring and service recovery | IT Operations Manager
21 |  | Data privacy breaches affecting user trust | Cybersecurity vulnerabilities | Exposure of user data | Reputational damage | 5 | 9 | 45 | H | Implement strong cybersecurity controls | Security Manager
22 |  | Platform maintenance and system updates | Routine system updates | Temporary service downtime | Operational inconvenience | 3 | 2 | 6 | L | Schedule maintenance during off-peak hours | IT Manager
23 |  | System scalability limitations during high order volumes | Rapid growth in order demand | System slowdowns | Technical inefficiency | 7 | 4 | 28 | M | Upgrade infrastructure capacity | IT Infrastructure Manager
24 |  | Data integration across fulfillment platforms | Multiple logistics systems exchanging data | Data inconsistencies | Operational errors | 5 | 6 | 30 | M | Improve system integration architecture | IT Manager
25 |  | Platform performance failure affecting order processing | System overload or technical failure | Order processing delays | Operational disruption | 5 | 8 | 40 | H | Increase server capacity and load balancing | IT Infrastructure Manager
26 |  | Large-scale logistics platform outage | Major system failure | Fulfillment operations halted | Severe operational disruption | 1 | 9 | 9 | L | Implement redundancy and failover systems | IT Operations Manager
27 |  | Regulatory reporting requirements for logistics operations | Government reporting obligations | Compliance workload | Administrative burden | 3 | 1 | 3 | L | Maintain compliance reporting systems | Compliance Officer
28 |  | Contract compliance review with logistics partners | Vendor contractual obligations | Operational review requirements | Administrative costs | 3 | 2 | 6 | L | Conduct regular contract audits | Procurement Manager
29 |  | Transparency requirements for logistics data reporting | Regulatory transparency requirements | Compliance adjustments | Operational complexity | 3 | 4 | 12 | L | Implement data governance policies | Compliance Officer
30 |  | Contract disputes with logistics providers | Disagreements over service agreements | Operational disruption | Legal costs | 3 | 6 | 18 | M | Strengthen contract management | Legal Manager
31 |  | Regulatory changes affecting cross-border shipping | New trade and shipping regulations | Compliance adjustments | Operational cost increases | 5 | 8 | 40 | H | Monitor regulatory updates | Compliance Officer
32 |  | Compliance risk related to customer data and shipping regulations | Privacy and shipping regulations | Compliance violations | Legal penalties and fines | 3 | 9 | 27 | M | Implement compliance audits | Compliance Officer

## RiskRegister2
Risk # | The Risk of/That | Likelihood Score | Impact Score
1 | Infrastructure upgrade costs for logistics technology | 3 | 2
2 | Vendor switching costs for logistics service providers | 3 | 4
3 | Logistics operating costs in human capital and warehouse infrastructure | 5 | 6
4 | Margin reduction due to price competition | 9 | 8
5 | Capital investment in logistics infrastructure | 5 | 9
6 | Process adjustments in fulfillment workflow | 3 | 1
7 | Limited human capital to support logistics operations | 5 | 2
8 | Third-party warehouse and delivery partner dependency | 5 | 4
9 | Integration between logistics systems and e-commerce platform | 7 | 6
10 | Fulfillment network disruption during peak demand periods | 7 | 8
11 | System failure or fulfillment network downtime | 3 | 9
12 | Limited competitive pressure from small platforms | 3 | 1
13 | Competitor promotional campaigns | 5 | 2
14 | Competitors introducing improved fulfillment capabilities | 5 | 4
15 | Competitors offering faster or lower-cost fulfillment services | 7 | 6
16 | Cost of lagging behind competitors with advanced logistics networks | 7 | 8
17 | Strong market competition from platforms with mature logistics networks | 9 | 9
18 | End-to-end commerce solution improving user experience | 7 | 1
19 | Dissatisfaction due to delivery delays | 5 | 4
20 | Logistic system and service failure affecting user experience | 5 | 8
21 | Data privacy breaches affecting user trust | 5 | 9
22 | Platform maintenance and system updates | 3 | 2
23 | System scalability limitations during high order volumes | 7 | 4
24 | Data integration across fulfillment platforms | 5 | 6
25 | Platform performance failure affecting order processing | 5 | 8
26 | Large-scale logistics platform outage | 1 | 9
27 | Regulatory reporting requirements for logistics operations | 3 | 1
28 | Contract compliance review with logistics partners | 3 | 2
29 | Transparency requirements for logistics data reporting | 3 | 4
30 | Contract disputes with logistics providers | 3 | 6
31 | Regulatory changes affecting cross-border shipping | 5 | 8
32 | Compliance risk related to customer data and shipping regulations | 3 | 9

## Heatmap
Impact | High | 9 | Risk26 | Risk11, Risk32 | Risk5, Risk21 |  | Risk17
|  | 8 |  |  | Risk20, Risk25, Risk31 | Risk10, Risk16 | Risk4
| Moderate | 6 |  | Risk30 | Risk3, Risk24 | Risk9, Risk15
|  | 4 |  | Risk2, Risk29 | Risk8, Risk14, Risk19 | Risk23
| Low | 2 |  | Risk1, Risk22, Risk28 | Risk7, Risk13
|  | 1 |  | Risk6, Risk12, Risk27 |  | Risk18
|  |  | 1 | 3 | 5 | 7 | 9
|  |  | Low | Moderate |  | High
Likelihood
[8 empty] | Risk # | The Risk of/That | Likelihood Score | Impact Score
[8 empty] | Risk1 | Infrastructure upgrade costs for logistics technology | 3 | 2 | 6
Threholds | [7 empty] | Risk2 | Vendor switching costs for logistics service providers | 3 | 4 | 12
Risk Score |  |  | Level | Color |  |  |  | Risk3 | Logistics operating costs in human capital and warehouse infrastructure | 5 | 6 | 30
1 - 15 |  |  | Low Risk | Green |  |  |  | Risk4 | Margin reduction due to price competition | 9 | 8 | 72
16-35 |  |  | Medium Risk | Yellow |  |  |  | Risk5 | Capital investment in logistics infrastructure | 5 | 9 | 45
36-81 |  |  | High Risk | Red |  |  |  | Risk6 | Process adjustments in fulfillment workflow | 3 | 1 | 3
[8 empty] | Risk7 | Limited human capital to support logistics operations | 5 | 2 | 10
[8 empty] | Risk8 | Third-party warehouse and delivery partner dependency | 5 | 4 | 20
[8 empty] | Risk9 | Integration between logistics systems and e-commerce platform | 7 | 6 | 42
[8 empty] | Risk10 | Fulfillment network disruption during peak demand periods | 7 | 8 | 56
[8 empty] | Risk11 | System failure or fulfillment network downtime | 3 | 9 | 27
[8 empty] | Risk12 | Limited competitive pressure from small platforms | 3 | 1 | 3
[8 empty] | Risk13 | Competitor promotional campaigns | 5 | 2 | 10
[8 empty] | Risk14 | Competitors introducing improved fulfillment capabilities | 5 | 4 | 20
[8 empty] | Risk15 | Competitors offering faster or lower-cost fulfillment services | 7 | 6 | 42
[8 empty] | Risk16 | Cost of lagging behind competitors with advanced logistics networks | 7 | 8 | 56
[8 empty] | Risk17 | Strong market competition from platforms with mature logistics networks | 9 | 9 | 81
[8 empty] | Risk18 | End-to-end commerce solution improving user experience | 7 | 1 | 7
[8 empty] | Risk19 | Dissatisfaction due to delivery delays | 5 | 4 | 20
[8 empty] | Risk20 | Logistic system and service failure affecting user experience | 5 | 8 | 40
[8 empty] | Risk21 | Data privacy breaches affecting user trust | 5 | 9 | 45
[8 empty] | Risk22 | Platform maintenance and system updates | 3 | 2 | 6
[8 empty] | Risk23 | System scalability limitations during high order volumes | 7 | 4 | 28
[8 empty] | Risk24 | Data integration across fulfillment platforms | 5 | 6 | 30
[8 empty] | Risk25 | Platform performance failure affecting order processing | 5 | 8 | 40
[8 empty] | Risk26 | Large-scale logistics platform outage | 1 | 9 | 9
[8 empty] | Risk27 | Regulatory reporting requirements for logistics operations | 3 | 1 | 3
[8 empty] | Risk28 | Contract compliance review with logistics partners | 3 | 2 | 6
[8 empty] | Risk29 | Transparency requirements for logistics data reporting | 3 | 4 | 12
[8 empty] | Risk30 | Contract disputes with logistics providers | 3 | 6 | 18
[8 empty] | Risk31 | Regulatory changes affecting cross-border shipping | 5 | 8 | 40
[8 empty] | Risk32 | Compliance risk related to customer data and shipping regulations | 3 | 9 | 27