## Risk Identification
Risk # | Date | The Risk of/That | Caused by | Resulting In | Consequence/Impact | Likelihood Score | Impact Score | Risk Score | Priority (H, M, L) | Mitigation | Risk Owner | Operational Status
1 | 04-03-2026 | Logistics Operation Failure (Negative) | Shopify's entry into logistics and fulfillment via acquisition may increase platform complexity and fees, making the platform less competitive for small-to-medium merchants. Competitors such as WooCommerce, BigCommerce, and Squarespace offer simpler, lower-cost alternatives. | Merchant Migration and measurable decline in active merchant accounts and monthly recurring revenue (MRR), weakening Shopify's market position and reducing the network effects that underpin its ecosystem value. | Financial: Revenue loss from reduced subscription and transaction fees. Operational: Lower GMV processed reduces partner and app-store revenues. Reputational: Negative perception among SME merchants amplifies churn. | 3 | 4 | 12 | H | 1. Maintain tiered pricing to protect SME affordability. 2. Communicate logistics integration as optional, not mandatory. 3. Monitor monthly churn rates; trigger review if merchant churn exceeds 5%. 4. Offer transition incentives to at-risk merchant segments. | Chief Commercial Officer | Monitor
2 | 04-03-2026 | Price Competition (Negative) | Entering the logistics sector brings Shopify into direct competition with Amazon, Fulfillment by Amazon (FBA), and other established logistics providers who can leverage scale to undercut Shopify's fulfillment pricing. | Margin compression on logistics services and pressure to discount subscription fees to retain price-sensitive merchants, reducing overall EBITDA and slowing profitability growth. | Financial: Reduced gross margin on logistics services; potential operating losses in fulfilment segment. Strategic: Erosion of competitive differentiation. Operational: Increased cost pressure on integration and infrastructure investments. | 4 | 4 | 16 | H | 1. Differentiate on integration quality and merchant experience rather than price alone. 2. Establish minimum acceptable margin thresholds (floor pricing policy). 3. Track competitor pricing quarterly; escalate if price gap exceeds 15%. 4. Pursue volume-based supplier contracts to reduce fulfilment COGS. | Chief Financial Officer | Active
3 | 04-03-2026 | Market share change through ecosystem expansion and omnichannel integration (Positive) | The acquisition of a logistics and fulfillment technology company enables Shopify to offer an end-to-end commerce solution. Combined with its existing payments, POS, and marketing tools, Shopify can attract enterprise merchants and international sellers who require integrated supply-chain capabilities. | Accelerated market share gains in the mid-market and enterprise segments, increased GMV, higher Average Revenue Per User (ARPU), and stronger international merchant growth — turning a competitive threat into a sustainable strategic advantage. | Strategic (Positive): Expanded addressable market and improved competitive moat. Financial (Positive): Higher-value merchant contracts increase MRR and ARPU. Operational: Integration complexity must be managed to realize the opportunity. Technology: Requires seamless API/data integration between platforms. | 3 | 5 | 15 | H | 1. Develop a phased omnichannel integration roadmap with clear milestones. 2. Assign dedicated enterprise sales team to capture mid-market opportunities. 3. Monitor market share growth quarterly; escalate investment if share gains exceed targets. 4. Conduct regular merchant satisfaction surveys to ensure integration quality. | Chief Strategy Officer | Opportunity

## KRIs
# | Risk Name | Problem Statement | KRI Metric (Leading Indicator) | Current Value | 🟢 Green (Optimized) | 🟡 Amber (Warning) | 🔴 Red (Critical)
1 | Logistics Operation Failure | Shopify's logistics acquisition may raise perceived complexity and cost for SME merchants. Competitors are actively targeting Shopify's core SME base with simpler, lower-cost alternatives. Requires monitoring now to prevent accelerating churn. | Monthly Merchant Churn Rate (%) [New cancellations ÷ Active merchants × 100] | ~0.8% (est.) | Churn Rate ≤ 1% (Normal attrition; no action required) | Churn Rate 1% – 3% (Elevated; investigate root cause and deploy retention campaigns) | Churn Rate > 3% (Critical; immediate executive escalation and pricing/product review)
2 | Price Competition from Larger Players | Entering logistics brings Shopify into direct competition with Amazon and established 3PLs who can sustain loss-leading pricing strategies. Fulfillment margin erosion could undermine the financial case for the acquisition. | Competitor Pricing Gap (%) [(Shopify fulfillment price - leading competitor average) ÷ leading competitor average × 100] | ~-1% premium (est.) | Price gap -5% - 5% (Competitive; differentiation sustains premium) | Price gap 5% – 10% (Warning; review pricing strategy and cost structure) | Price gap > 10% (Critical; immediate repricing or promotional response required)
3 | Market Share via Ecosystem Expansion | Shopify has an opportunity to capture enterprise and mid-market merchants who need integrated logistics alongside commerce tools. The acquisition window is time-sensitive as competitors are building similar capabilities. Requires proactive monitoring to maximize share gains. | Market Growth Rate — Mid-Market Segment (%) [New mid-market/enterprise merchant sign-ups QoQ] | ~4% QoQ (est.) | Growth ≥ 5% QoQ (On track; continue investment) | Growth 2% – 5% QoQ (Below target; review go-to-market and integration readiness) | Growth < 2% QoQ (Opportunity at risk; immediate strategic review and resource reallocation)

## Risk Scoring Legend
RISK SCORING LEGEND
Score Range | Priority Level | Description
15–20 | H | HIGH – Immediate action required
9–14 | M | MEDIUM – Monitor and mitigate
1–8 | L | LOW – Accept and log